Accreditation Scheme T&F Group

Update Report to Board - 27.11.19

Activities:

Since the last meeting we have kept to our plan to continue towards the conclusion of pilot 1 and begin preparations for pilot 2.

- The Accreditation group managed to make c12/13 submissions or part submissions for pilot 1

- We have individually reviewed all submissions and run 4 online panels.

- Final statistics on successful submissions, at what level and those not yet awarded are still being collated at the time of writing and will be updated verbally at Board.

- Evaluative feedback on and ideas for improving, the guidance for applicants and the reviewing process have been provided.

- The Accreditation T&F group met as planned in October and made plans for recruiting to and running pilot 2 in January

- The AT&F Group also actioned the creating of guidance materials and procedural templates to be drafted. A progress check to comment on initial drafts will take place on 4th December at a second all day face to face meeting in London.

- The deadline for volunteers for pilot 2 was Friday 22nd November. We agreed on a maximum of 24 and were aiming for a mixture of AM/SAM as well as a mixture of practitioner roles and submission formats (ie written/verbal).

- The number recruited so far is just 9 and 5 of those are from Ulster and just two appear to be AM applicants. However, we are pleased to see 2 Assessment Centre Manager applicants and 3 people preferring to submit verbally.

- We are looking to spread the net a little wider and would request more Directors to consider applying and more importantly, encouraging members of their teams to apply at AM level.

- We have asked them to confirm willingness to pay £50 (stressing that this is a significant discount from the likely final fee).

- We have also asked them to commit to a tight timescale that should enable us to stay on target to announce a launch date at AC20.

- Several of the wider Accreditation Group who have taken part on the Panels as Reviewers have expressed willingness to continue in this capacity for pilot 2 and beyond.

- I supported two panels directly, Chairing one and reading/reviewing the submissions in support of the other. There was a considerable level of agreement within the panels as to what constituted award and not yet awarded. This is extremely positive and ongoing sharing of decision-making to help with moderation needs to continue.

Further points to note:

Once pilot 2 is underway there remain a considerable number of tasks to perform (in no particular order):

- Costing the scheme

- Evaluating pilot 2 and finalising support mechanisms

- Finalising guidance materials

- Finalising process systems

- Promotion of the scheme

Comments and/or questions from Directors are welcome.

Paddy Turner

Accreditation Task & Finish Group Chair

November 2019